## Team Status
Meeting date | Developer | Working Module | Start Date | Expected Date to complete | Completed Date | Remarks
2018-04-28 | Anju | Chitty Backend | 2018-04-25 | Yet to compute
| Akhil | Chitty Frontend | 2018-04-25 | Yet to compute
| Anu | Advance Backend | 2018-04-25 | 2018-05-02 | 2018-05-02 |  | Completed / Going on
| Dinith | Advance Frontend | 2018-04-25 | 2018-05-02 | 2018-05-02 |  | Membership
| Sreeja | MasterFiles |  | 2018-05-14 |  |  | Deposit
| Soumya | User locking |  | Yet to compute |  |  | Loans
Chitty
2018-05-05 | Anju | Chitty Backend | 2018-04-25 | 2018-05-25 |  | selection procedures required from Anitha / Shaji sir | Advance
| Akhil | Chitty Frontend | 2018-04-25 | 2018-05-25 |  |  | Masterfiles
| Anu | Investment Backend | 2018-04-25 | 2018-05-10 |  |  | UserLocking
| Dinith | Investment Frontend | 2018-04-25 | 2018-05-10 |  |  | Investment
| Sreeja | MasterFiles |  | 2018-05-14
| Soumya | User locking / Amount transfer |  | Yet to compute

## Infrastructure
Task | Status
Identity | Completed | Code Review
Common interceptor for User locking | Completed | Weeky scrum
Set claim functionality | In progress | Team support
Open in new tab functionality | Not started
Logging all requests and response | Not started
Host in cloud | Not started
Try with new core 2.1 | Not started
Design changes | Not started
Test with multi-tenant with different configs | Not started